## Sheet1
PROJECT START TO COMPLETION 2016 TO 2017
ACTIVITY DESCRIPTION | BUILDING "A" |  | BUILDING "B" | BUILDING "C"
| POOL AREA |  | CENTER AREA | GYMNASIUM AREA
| NATATORIUM |  | CLASSROOMS, OFFICE | GYMNASIUM
DEMOLITION | Start May 23 finish June 15, 2016
DEMOLITION |  |  | Start June 15 finish July 15, 2016
DEMOLITION |  |  |  | Start August 1 finish August 29, 2016
SHEATHING | Start May 30 finish June 20, 2016
SHEATHING |  |  | Start July 11 finish July 29 , 2016
SHEATHING |  |  |  | Start August 15 finish September 5, 2016
MOCK UP EIFS SYSTEM | Start May 23 finish June 24, 2016
EXTERIOR INSULATION FINISH SYSTEM | Start June 5 finish August 13, 2016
EXTERIOR INSULATION FINISH SYSTEM |  |  | Start July 25 finish Octob 10, 2016
EXTERIOR INSULATION FINISH SYSTEM |  |  |  | Start September 4 finish December 30, 2016
Supervisor : upon contract will be assign
STO MANUFACTURER SYSTEM |  | Foreman : Juan Carlos Escobar ; Exterior Insulation Finish System 20 years of solid experience
STO THERM RAINSCEEN II |  | Foreman : Charly Giron; Sheathing 5 years experience
Foreman : Godofredo Becerra; Demolition 6 years

## Page 2
THREE WEEK LOOK AHEAD SCHEDULE Page 2 0f 2
CONTRACTOR | ACTIVITY DESCRIPTION | WEEK OF: |  |  |  | 2013-07-28 |  |  | WEEK OF: |  |  |  | 2013-08-04 |  |  | WEEK OF: |  |  |  | 2013-08-11
|  | 2013-07-28 | 2013-07-29 | 2013-07-30 | 2013-07-31 | 2013-08-01 | 2013-08-02 | 2013-08-03 | 2013-08-04 | 2013-08-05 | 2013-08-06 | 2013-08-07 | 2013-08-08 | 2013-08-09 | 2013-08-10 | 2013-08-11 | 2013-08-12 | 2013-08-13 | 2013-08-14 | 2013-08-15 | 2013-08-16 | 2013-08-17
|  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
Install CMU & Brick at control Bldg. | bar: 2013-08-07 to 2013-08-09; 2013-08-12 to 2013-08-16
ADM | Install rebar and pour house keeping at bldg.Pads | bar: 2013-08-07 to 2013-08-09
NORAIR/HARTWELL | Install CU Duct Bank "A" to plant | [21 empty] | 1899-12-31 | bar: 2013-08-05 to 2013-08-09
NORAIR/HARTWELL | Install Duct Banks at Southeast of plant | bar: 2013-08-05 to 2013-08-09; 2013-08-12 to 2013-08-16
LEGEND : NON WORK DAY
ACTIVE WORK PERIOD
WEATHER DELAY DAY
HOLIDAY