## Cover Sheet
Application and Certificate for Payment
TO OWNER: | Naval Facilities Engineering Command |  | PROJECT: | Design Building B1652 |  |  | APPLICATION No. |  | 1
| Patuxent, MD |  |  | Inteiror and HVAC Repairs |  |  | PERIOD FROM |  | 2015-03-20 | Distribution to:
|  |  |  | Patuxent Naval Air Station |  |  | PERIOD TO |  | 2015-05-30 | OWNER
[7 empty] | CONTRACT DATE: |  |  | ARCHITECT
FROM CONTRACTOR: | Million Construction Inc | [5 empty] | PROJECT #s : |  | N40080-3858506 | CONTRACT
| 8917 Burke Lake Rd |  | VIA ARCHITECT: | Consolidated Engineering LLC |  |  | ORDER # |  |  | FIELD
| Springfield, VA 22151 |  |  | 3014 Mitchellville Rd | [5 empty] | OTHER
| FEIN# 54-2001358 |  |  | Bowie, MD 20716
BILL TO:
The undersigned Contractor certifies that to the best of the Contractor's knowledge, information
CONTRACTOR'S APPLICATION FOR PAYMENT |  |  |  | and belief the Work covered by this Application for Payment has been completed in accordance
with the Contract Documents, that all amount have been paid by the Contractor for Work for
Application is made for payment, as show below, in connection with the Contract. |  |  |  | which previous Certificates for Payment were issued and payments received from the Owner, and
Continuation Sheet, AIA Document G703, is attached |  |  |  | that current paymet shown herein is now due.
1. ORIGINAL CONTRACT SUM..…………………………………………. |  |  | 1026000 | CONTRACTOR: |  | Million Construction Inc
2. NET CHANGE BY CHANGE ORDERS………………………………… |  |  | 0 | [7 empty] | 6037.5
3. CONTRACT SUM TO DATE (Line 1+/-2)……………….. |  |  | 1026000 | By: _____________________________________________ |  |  |  | Date: ________________________
4. TOTAL COMPLETED AND STORED TO DATE(Column G on G703) |  |  | 0 | State of: | Virginia | [5 empty] | 7260 | 141.3223
5. RETAINAGE: |  |  |  | County of: | Fairfax
a. 5.0% of Completed Work |  |  |  | Subscribed and sworn to before | [6 empty] | 33.2645
(Column D + E on G703) |  |  |  | me this __________________ day of __________________________
b. 5.0% of Stored Material |  |  |  | Notary Public: | [6 empty] | 7245
(Column F on G703) |  |  |  | My Commission Expires:
Total Retainage (Line 5a + 5b or Total in Column I of G703) |  |  | 0 | ARCHITECT'S CERTIFICATION
6. TOTAL EARNED LESS RETAINAGE…………..…………………….. |  |  | 0 | In accordance with the Contract Document, based on on-site observations and the data comprising
(Line 4 Less Line 5 Total) |  |  |  | this application, the Architect certifies to the Owner that to the best of the Architect's knowledge,
7. LESS PREVIOUS CERTIFICATES FOR PAYMENT……… |  |  | 0 | information and belief the Work has progressed as indicated, the quality of the Work is in accordance
(Line 6 from prior Certificate) |  |  |  | with the Contract Documents, and the Contractor is entitled to payment of AMOUNT CERTIFIED
8. CURRENT PAYMENT DUE……………………...………………………….. |  |  | 0 | AMOUNT CERTIFIED………………………………………$__________________________
9. BALANCED TO FINISH, INCLUDING RETAINAGE……….. |  |  |  | (Attach explanation if amount certified differs from the amount applied for, Initial all figures on this
(Line 3 minus Line 6 Total) |  | 1026000 |  | Application and on the Continuation Sheet that are changed to conform with the amount certified.)
CHANGE ORDER SUMMARY |  | ADDITIONS | DEDUCTIONS | ARCHITECT
Totals changes approved in previous months |  |  |  | By: _____________________________________________ |  |  |  | Date: ___________________________
Total approved this Month |  | 0 | 0 | This Certified is not negotiable. The AMOUNT CERTIFIED is payable only to the Contractor named
TOTALS |  | 0 | 0 | herein. Issuance, payment and acceptance of payment are without perjudice to any rights of the
NET CHANGES by Change Order |  | 0 |  | Owner or Contractor under this Contract.

## BUILDING 75
CONTINUATION SHEET
SCHEDULE OF VALUES
A | B | C | D |  | F | G |  | H | I
ITEM No. | DESCRIPTION OF WORK | SCHEDULED VALUE | WORK COMPLETED |  |  | TOTAL COMPLETED AND STORED TO DATE (D+E+F) | % (G/C) | BALANCE TO FINISH (C-G) | RETAINAGE
|  |  | PREVIOUS APPLICATIONS | THIS APPLICATION
|  |  |  | WORK IN PLACE | STORED MATERIALS (NOT IN D OR E) |  |  |  |  | Sub's Contract Amount | Subcontractor | SOV's System 42
1 | GENERAL CONDITIONS | [9 empty] | System 42
1.01 | Mobilization | 10000
1.02 | Insurance | 69500
1.03 | Project Management | 39500
1.04 | Supervisor / Foreman | 41000
1.05 | Mock - Up | 20000 | [9 empty] | 180000
2 | Demolition
2.01 | Demolition Tools | 15000
2.03 | Demolition Equipment | 29500
2.04 | Demolition Labor | 59500
7 | Exterior Insulation Finish System
7.01 | Material | 275000
7.02 | Equipment | 69500
7.03 | Labor | 288000
9 | Gysump Sheathing
| Material | 39500
| Labor | 59500
| Equipment | 10500
| TOTALS | 1026000 | 0