## Sheet1
CHANGE ORDER |  |  | PROJECT NAME: | RENOVATION TO THE MVA GAITHERSBURG BRANCH OFFICE |  |  | CONTRAC No.: V-GAT-07040-C
|  |  | CLIENT'S NAME AND ADDRESS: | MOTOR VEHICLE ADMINISTRATION OF THE MARYLAND DEPARTMENT TRANSPORTATION - 6601 RITCHIE HIGHWAY, NE OIR BUILDING, ROOM 309, GLEN BURNIE, MD 21062 |  |  | PROJECT LOCATION: 115 METROPOLITAN GROVE ROAD, GAITHERSBURG, MD 20878
MVA CO # | System "42" COR # | DESCRIPTION |  |  | DATE SUBMITTED | AMOUNT OF CHANGE | DATE OF RESPONSE | AMOUNT APPROVED | DELAY IMPACT | BILLED | REMARKS
Appl. #4 Allow #5 | 1 | Extrawork : Curb and Gutter/ Sidewalk/ Ramps/ Full Depth Patch |  |  | 2008-09-23 | 17703 |  | 17703 | No | 17703 | Paid - Appl 4 - Set 2008 | 17703
Appl. #6 Allow #5 | 1 | Furnish and Install Drywall in Conference Room and Adm Assisst. 1 &2 |  |  | 2008-09-30 | 2592.6 |  | 2592.6 |  | 2592.6 |  | 2592.6
| 2 | Furnish and Labor and Material to Install Cold Applied Roof in lieu of Hot Asphalt Roof |  |  | 2008-10-09 | 127374.26 | [7 empty] | 926.016
| 3 | Tree and Stump Removal Employee Parking Lot |  |  | 2008-11-05 | 7857 | [5 empty] | 7300 | Ridgely's Services LLC P.O. Box 824 Frederick, MD 21705 301-662-6128 | 2008-12-15
| 4 | Two storage sheds |  |  | 2008-11-15 | 10226 | [5 empty] | 10226 | System 42 | 2008-12-15
| 4R1 | Two storage sheds |  |  | 2008-12-30 | 8963
| 4R2 | Two storage sheds |  |  | 2009-03-09 | 8586.65
| 5 | Add GAP MB Topcoat to Built Up Roof |  |  | 2008-11-15 | 48059 |  |  |  |  | Per Architect Request | 44653.85 | Rich Roofing | 2008-12-15
| 5R | Revised Built Up Roof Surface Coating |  |  | 2008-12-05 | 19886 | 2009-03-04 | 14000 |  |  | Per Architect Request | 17540.33 937.17 | Rich Roofing System 42 Inc | 2008-12-15
Appl. #8 Allow. #5 | 6 | Wedge and Level Asphalt for Winter |  |  | 2008-11-11 | 3985 | 2009-02-10 | 3985 |  | 3985 | Paid throught Appl. 8
| 7 | Increase Base Flashing Framing Height |  |  | 2008-11-11 | 6524 | 2008-12-22 |  |  |  | RFI 23 Please provide the subcontractor breakdown
Appl. #7 Allow. #5 | 7R | Increase Base Flashing Framing Height |  |  | 2008-12-30 | 5493 | 2008-12-20 | 5493 |  | 5493 | Paid throught Appl. 7
| 8 | Demo and Replace North Main Entrance |  |  | 2008-11-14 | 10731 |  |  |  |  | RFI 25
Appl. #7 Allow. #5 | 8R | Demo and Replace North Main Entrance |  |  | 2008-12-30 | 9290 | 2009-01-09 | 9290 |  | 9290 | Paid throught Appl. 7 | 14783
| 9 | New Concrete Ramp at Main Entrance |  |  | 2008-11-14 | 4408 | 2008-12-22 |  |  |  | Revised
Appl. #8 Allow. #5 | 9R1 | New Concrete Ramp at Main Entrance |  |  | 2008-12-30 | 4170 | 2009-02-10 | 4170 |  | 4170 | Paid throught Appl. 8
| 10 | Sand Test Course Surface Paving |  |  | 2008-11-15 | 1202 | 2008-12-22 | 1202.18
| 11 | Telephone & Data Cabling -Allowance |  |  | 2008-12-17 | 89692 |  |  |  |  | Revised
| 11R1 | Telephone & Data Cabling -Allowance |  |  | 2009-01-15 | 27284 | [5 empty] | 8155
| 12 | Relocate Wall at Law Test Area |  |  | 2008-12-11 | 4354 | 2008-12-22 | 4354 |  |  | Sketch 2 , Nov 25, 2008 |  | Ceca System 42 Inc
| 12R1 | Relocate Wall at Law Test Area |  |  | 2008-12-30 | 4108
| 13 | Acoustical Ceiling Grid Direction |  |  | 2008-12-11 | 2177 | 2008-12-22 |  |  |  | RFI - 27
| 14 | Casework - Allowance |  |  | 2009-01-14 | 190614
| 15 | Millwork Allowance Kitchen Cabinets |  |  | 2009-01-23 | 12168 |  |  |  |  | Revised
| 15 R1 | Millwork Allowance Kitchen Cabinets |  |  | 2009-01-30 | 11064 |  | 3884.98 |  |  | No included Countertop
3884.98
Appl. #9 Allow. #5 | 16 | Repair Sewer Clogged Line |  |  | 2009-01-28 | 11096 | 2009-03-10 | 11096 |  | 11096 | Paid throught Appl. 9
| 17 | Change to install nine (9) drops for data and/or telephone in Conference Room and Admin Asst-1 and Asst-2 per SKE-1 |  |  | 2009-03-09 | 864.07 |  | 864.07 |  |  | Approved |  | 225
| 18 | Remove Eighty-Four (84) Smoke Detectors and Nine (9) Indicator Lights and reinstall after new ceiling tile |  |  | 2009-03-09 | 5657.7279 |  | 5657.73 |  |  |  |  | 11.25
| 19 | Install Quad Receptacles in Comp Closet and Conf Room and data drops in Office-1, -2 and -3 per SKE-3 and SKE-6 |  |  | 2009-03-09 | 1229.31 |  | 1229.31 |  |  |  |  | 236.25
| 20 | Remove and install wiring and conduit for two (2) extra stations in the Law Test Area per SKE-2 |  |  | 2009-03-09 | 1290.8004 |  | 1290.8 |  |  |  |  | 5.9062
| 21 | Install Nine (9) Duplex Receptacles in Conf. Room on new circuit per SKE-1 |  |  | 2009-03-09 | 1875.258 |  | 1875.26 |  |  |  |  | 242.1562
Appl. #9 Allow. #5 | 22 | Verizon Invoice for Relocate Phone and Fax Lines |  |  | 2009-03-09 | 242.1562 | 2009-03-10 | 242.16 |  | 242.16 | Paid throught Appl. 9 |  | 230.9062
| 23 | Installation of Data/Telephone |  |  | 2009-03-06 | 11435.3607 |  | 11435.36 |  |  | This is part of Allowance 4
| 24 | Add 5'-0" High knee wall for Rest Area adjacent to Kitchen |  |  | 2009-03-09 | 2175.3703 |  | 2175.37
| 25 | Relocate Furniture to Various Offices and Demo Temporary Wall @ Specialty Services |  |  | 2009-03-09 | 939.76 |  | 939.76
| 26 | Remove Door D18 and Close In GWB wall as per Sketch-5 |  |  | 2009-03-09 | 208.405 |  | 208.41
| 27 | Remove Door D19 and Close In GWB wall as per Sketch-5 |  |  | 2009-03-06 | 208.41 |  | 208.41
| 28 | Change VCT Flooring to Carpet in Admin. Conference Room, Admin. Asst. 1 and 2 per RFI 37 |  |  | 2009-03-05 | 7920.1237
| 29 | Demo and Cap existing lawn sprinkler line in Stock Room |  |  | 2009-03-06 | 2044.875 |  | 2044.88
| 30 | Trouble-shoot and Repair Existing Annunciator Panel-in Vestibule |  |  | 2009-03-20 | 769.52 |  | 769.52
[6 empty] | 32583.8474 |  | 21148.4866

## Change Order Log
CHANGE ORDER |  |  | PROJECT NAME: | RENOVATION TO THE MVA GAITHERSBURG BRANCH OFFICE |  |  | CONTRAC No.: V-GAT-07040-C
|  |  | CLIENT'S NAME AND ADDRESS: | MOTOR VEHICLE ADMINISTRATION OF THE MARYLAND DEPARTMENT TRANSPORTATION - 6601 RITCHIE HIGHWAY, NE OIR BUILDING, ROOM 309, GLEN BURNIE, MD 21062 |  |  | PROJECT LOCATION: 115 METROPOLITAN GROVE ROAD, GAITHERSBURG, MD 20878
MVA CO # | System "42" COR # | DESCRIPTION |  |  | DATE SUBMITTED | AMOUNT OF CHANGE | DATE OF RESPONSE | AMOUNT APPROVED | DELAY IMPACT | BILLED | Subcontractor | REMARKS
Appl. #4 Allow #5 | 1 | Extrawork : Curb and Gutter/ Sidewalk/ Ramps/ Full Depth Patch MATTERN CO. |  |  | 2008-09-23 | 17703 |  | 17703 |  | 17703 | 17703 | Paid - Appl 4 - Set 2008 | 17703
Appl. #12 Allow #2 | 1 | Furnish and Install Drywall in Conference Room and Adm Assisst. 1 &2 SYSTEM "42" INC |  |  | 2008-09-30 | 2592.6 | 2009-05-08 | 2280 |  | 2592.6 |  |  | 2592.6
| 2 | Furnish and Labor and Material to Install Cold Applied Roof in lieu of Hot Asphalt Roof RICH ROOFING |  |  | 2008-10-09 | 127374.26 | [8 empty] | 926.016
| 3 | Tree and Stump Removal Employee Parking Lot MATTERN CO. |  |  | 2008-11-05 | 7857 |  |  |  |  | 7000 |  | 7300 | Ridgely's Services LLC P.O. Box 824 Frederick, MD 21705 301-662-6128 | 2008-12-15
Appl. 16 | 3A | Tree and Stump Removal Employee Parking Lot MATTERN CO. |  |  | 2008-11-05 | 7857 | 2009-08-10 | 11193
| 4 | Two storage sheds MR, SHEDS INC |  |  | 2008-11-15 | 10226 | [6 empty] | 10226 | System 42 | 2008-12-15
| 4R1 | Two storage sheds MR, SHEDS INC |  |  | 2008-12-30 | 8963
Appl. #12 Allow #2 | 4R2 | Two storage sheds MR, SHEDS INC |  |  | 2009-03-09 | 8586.65 | 2009-05-08 | 8586.65 |  |  | 7470.88
| 5 | Add GAP MB Topcoat to Built Up Roof - RICH ROOFING |  |  | 2008-11-15 | 48059 | [5 empty] | Per Architect Request | 44653.85 | Rich Roofing | 2008-12-15
| 5R | Revised Built Up Roof Surface Coating - RICH ROOFING |  |  | 2008-12-05 | 19886 | 2009-03-04 | 14000 |  |  | 14389.11 | Per Architect Request - See CO.# 31B | 17540.33 937.17 | Rich Roofing System 42 Inc | 2008-12-15
Appl. #8 Allow. #5 | 6 | Wedge and Level Asphalt for Winter MATTERN CO. |  |  | 2008-11-11 | 3985 | 2009-02-10 | 3985 |  | 3985 | 3700 | Paid throught Appl. 8
| 7 | Increase Base Flashing Framing Height SYSTEM "42" INC |  |  | 2008-11-11 | 6524 | 2008-12-22 |  |  |  |  | RFI 23 Please provide the subcontractor breakdown
Appl. #7 Allow. #5 | 7R | Increase Base Flashing Framing Height SYSTEM "42" INC |  |  | 2008-12-30 | 5493 | 2008-12-20 | 5493 |  | 5493 |  | Paid throught Appl. 7
| 8 | Demo and Replace North Main Entrance |  |  | 2008-11-14 | 10731 | [5 empty] | RFI 25
Appl. #7 Allow. #5 | 8R | Demo and Replace North Main Entrance MATTERN CO. |  |  | 2008-12-30 | 9290 | 2009-01-09 | 9290 |  | 9290 | 8500 | Paid throught Appl. 7 | 14783
| 9 | New Concrete Ramp at Main Entrance |  |  | 2008-11-14 | 4408 | 2008-12-22 |  |  |  |  | Revised
Appl. #8 Allow. #5 | 9R1 | New Concrete Ramp at Main Entrance MATTERN CO. |  |  | 2008-12-30 | 4170 | 2009-02-10 | 4170 |  | 4170 | 3343 | Paid throught Appl. 8
Appl. #12 Allow #2 | 10 | Sand Test Course Surface Paving MATTERN CO. |  |  | 2008-11-15 | 1202 | 12/22/2008 05/08/09 | 1202 |  |  | 920 |  |  | 7625.19
| 11 | Telephone & Data Cabling -Allowance BROWN COMM. |  |  | 2008-12-17 | 89692 | [5 empty] | Revised
Appl 12 Appl. 13 | 11R1 | Telephone & Data Cabling -Allowance BROWN COMM. |  |  | 2009-01-15 | 27284 |  | 27841.0868 |  | 11435.36 | 15146.51 | Appl. 8 was paid $6,500.00 Appl. 9 was paid $4,935.36 | 35996.0868 | 11435.36
| 12 | Relocate Wall at Law Test Area SYSTEM "42" INC |  |  | 2008-12-11 | 4354 | 2008-12-22 | 4354 |  |  |  | Sketch 2 , Nov 25, 2008 |  | Ceca System 42 Inc
| 12R1 | Relocate Wall at Law Test Area SYSTEM "42" INC |  |  | 2008-12-30 | 4108
Appl. #12 Allow #2 | 13 | Acoustical Ceiling Grid Direction SYSTEM "42" INC |  |  | 2008-12-11 | 2177 | 12/22/2008 05/08/09 | 1864.93 |  |  | 1732.8 | RFI - 27
Allow. #1 | 14 | Casework - Allowance MARYLAND CORRECTIONAL |  |  | 2009-01-12 | 190614 | 2009-01-13 | 185948.73 |  |  | 172774.67
| 15 | Millwork Allowance Kitchen Cabinets |  |  | 2009-01-23 | 12168 | [5 empty] | Revised
| 15 R1 | Millwork Allowance Kitchen Cabinets |  |  | 2009-01-30 | 11064 | [5 empty] | No included Countertop
Appl. #10 Allow. #5 | 15 R2 | Millwork Allowance Kitchen Cabinets SYSTEM "42" |  |  | 2009-01-30 | 3884.98 | 2009-02-03 | 3884.98 |  |  |  | Not Included Counter Top
Appl. #9 Allow. #5 | 16 | Repair Sewer Clogged Line PARAMOUNT PLUMBING |  |  | 2009-01-28 | 11096 | 2009-03-10 | 11096 |  | 11096 | 10825 | Paid throught Appl. 9
Appl. #10 Allow. #5 | 17 | Change to install nine (9) drops for data and/or telephone in Conference Room and Admin Asst-1 and Asst-2 per SKE-1 CECA |  |  | 2009-03-09 | 864.07 | 2009-04-09 | 610.39 |  |  | 643.62 | Approved |  | 225
Appl. #10 Allow. #5 | 18 | Remove Eighty-Four (84) Smoke Detectors and Nine (9) Indicator Lights and reinstall after new ceiling tile CECA |  |  | 2009-03-09 | 5657.7279 | 2009-04-09 | 5657.73 |  |  | 4551.42 |  |  | 11.25
Appl. #10 Allow. #5 | 19 | Install Quad Receptacles in Comp Closet and Conf Room and data drops in Office-1, -2 and -3 per SKE-3 and SKE-6 CECA |  |  | 2009-03-09 | 1229.31 | 2009-04-09 | 1229.31 |  |  | 988.93 |  |  | 236.25
| 20 | Remove and install wiring and conduit for two (2) extra stations in the Law Test Area per SKE-2 CECA |  |  | 2009-03-09 | 1290.8004 | 2009-04-09 | 0 |  |  | 984 | Work was covered under previous approved change order |  | 5.9062
Appl. #10 Allow. #5 | 21 | Install Nine (9) Duplex Receptacles in Conf. Room on new circuit per SKE-1 CECA |  |  | 2009-03-09 | 1875.258 | 2009-04-09 | 1756.2 |  |  | 1742.4 |  |  | 242.1562
Appl. #9 Allow. #5 | 22 | Verizon Invoice for Relocate Phone and Fax Lines MVA |  |  | 2009-03-09 | 242.1562 | 2009-03-10 | 242.16 |  | 242.16 |  | Paid throught Appl. 9 |  | 230.9062
| 23 | Installation of Data/Telephone BROWN COMMUNICATION |  |  | 2009-03-06 | 11435.3607 | [5 empty] | This is part of Allowance 4 Incl CO#11R1
| 24 | Add 5'-0" High knee wall for Rest Area adjacent to Kitchen MILLION CONSTRUCTION |  |  | 2009-03-09 | 2175.3703 |  |  |  |  | 2021.25
Appl. #10 Allow. #5 | 25 | Relocate Furniture to Various Offices and Demo Temporary Wall @ Specialty Services HEBERT CONSTRUCTION |  |  | 2009-03-09 | 939.76 | 2009-04-09 | 939.76 |  |  | 700
| 26 | Remove Door D18 and Close In GWB wall as per Sketch-5 MILLION CONSTRUCTION |  |  | 2009-03-09 | 208.405 | 2009-04-09 | 0 |  |  | 193.64 | Removel of Door D18, we will check the site condition, no instruction to that effect were given
Appl. #12 Allow #2 | 26A | Remove Door D13 and close-in GWB wall as per sketch-5 MILLION CONSTRUCTION |  |  | 2009-04-15 | 208.41 | 2009-05-08 | 208.4
Appl. #10 Allow. #5 | 27 | Remove Door D19 and Close In GWB wall as per Sketch-5 MILLION CONSTRUCTION |  |  | 2009-03-06 | 208.41 | 2009-04-09 | 208.4 |  |  | 193.64
| 28 | Change VCT Flooring to Carpet in Admin. Conference Room, Admin. Asst. 1 and 2 per RFI 37 INNERSPACE |  |  | 2009-03-05 | 7920.1237 |  |  |  |  | 7359 | Carpet And VCT Take-off shows that there is a very small amount of additional carpet-InnerSpace to re-evaluate
Appl.16 | 29 | Demo and Cap existing lawn sprinkler line in Stock Room PARAMOUNT PLUMBING |  |  | 2009-03-06 | 2044.875 | 2009-11-04 | 2044.88 |  |  | 1900
Appl. #10 Allow. #5 | 30 | Trouble-shoot and Repair Existing Annunciator Panel-in Vestibule - MVA |  |  | 2009-03-20 | 769.52 | 2009-04-09 | 769.52 |  |  | 715
| 31 | Furnish and Install Cap Sheet for Built-up Roof RICH ROOFING |  |  | 2009-03-31 | 35909.27 | 2009-04-02 | 0 |  |  |  | See CO 31A
| 31A | Furnish and Install Cap Sheet for Built-up Roof RICH ROOFING |  |  | 2009-04-21 | 28443.75 | 2009-04-09 | 0 |  |  |  | This CO is not approved as the Cap Sheet is covered under Base Bid
Appl 15 Allow #2 #4 | 31B | Furnish and Install Cap Sheet for Built-up Roof RICH ROOFING |  |  | 2009-04-23 | 42443.75 | 2009-04-24 | 42443.75 |  |  | 27750 | Incl. CO. 5R for $14,000.00
| 32 | Remove Winterization Paving MATTERN CONSTRUCTION |  |  | 2009-04-15 | 1195 |  |  |  |  | 1059.87
| 33 | Remove existing sidewalk and Install ADA compliant Ramp at Storage Door at Rear of Building MATTERN CONSTRUCTION |  |  | 2009-04-15 | 9268.9 | IT WAS PREPARE FOR TYRONE BUT IN THE MEETING THE OWNER CHANGE MIND AND DELETED |  |  |  | 8560
Appl 14 Allow 2 | 33 | Furnish Labor and Material to Patch Areas prior to the Asphalt Paving as designated on Drawings provided by MVA MATTERN CONSTRUCTION |  |  | 2009-04-24 | 8711.23 | 2009-04-27 | 8711.23 |  |  | 8094.06
Appl. 13 Allow #2 | 34 | Remove Existing sidewalk and install ADA compliant Ramp at Storage Door at Rear of Building MATTERN CONSTRUCTION |  |  | 2009-04-24 | 2063.31 | 2009-04-24 | 2063.31
Appl. 13 Allow #2 | 35 | Demo Existing Casework SYSTEM "42" INC |  |  | 2009-05-12 | 15390.83 | 2009-05-13 | 15390.83
Appl 14 Allow 2 | 36 | Additional Labor Cost for Installation of Casework on Sunday MCE |  |  | 2009-05-13 | 3835.76 | 2009-05-15 | 3835.76 | [5 empty] | 182082.26
Appl 14 Allow 2 | 37 | Additional Labor & Material Cost to Modify Door D07, D24 and D14 SYSTEM "42" INC |  |  | 2009-06-09 | 1380.04 | 2009-06-22 | 1380.04
| 38 | Additional Labor & Material for Requested Sitework MATTERN CONSTRUCTION |  |  | 2009-06-09 | 3038.25
Appl 15 Allow 2 | 39 | Additional Labor to Move and Relocate Furniture HEBERT CONSTRUCTION |  |  | 2009-06-09 | 1506.75 | 2009-06-22 | 1506.75
Appl 15 Allow 2 | 40 | Additional Labor & Material to Perform Various Tasks as requested by MVA SYSTEM "42" INC |  |  | 2009-07-13 | 2598.34 | 2009-07-16 | 2598.34
Appl 15 Allow 2 | 41 | Additional Labor & Material to Intsall New Door and Plywood in new Storage Room SYSTEM "42" INC |  |  | 2009-07-13 | 2510.83 | 2009-07-16 | 2510.83
| 42 | Additional Labor & Material to Paint Nine (9) Exisiting Window Frames to match Aluminum Storefront SYSTEM"42" INC |  |  | 2009-07-13 | 651.76 | [5 empty] | MVA decided not to do
| 43 | Additional Labor & Material to Provide Battery/Electric Powered Sensors for Existing Toilet Flush Valves and Faucets PARAMOUNT PLUMBING |  |  | 2009-07-13 | 21512.89 | 2009-08-10 | 23153.25
Appl 15 Allow 2 | 44 | Additional Labor & Material to Provide Receptacles above the six (6) CECA, LLC |  |  | 2009-07-13 | 1142.75 | 2009-07-16 | 1142.75
| 45 | Labor and Material to Provide Additions and Correction to the Casework MCE |  |  | 2009-07-28 | 12961.95
Appl. 16 | 45A | Labor and Material to Provide Additions and Correction to the Casework- REVISED MCE |  |  | 2009-08-03 | 10625.82 | 2009-08-03 | 10625.82
Appl. 16 | 46 | Additional Cost to Relocate Security Safe from existing DELPS office to new Safe Room - SAFE & SECURITY SYS. |  |  | 2009-07-28 | 688.8 | 2009-08-10 | 688.8
| 47 | Additional Cost to Repair EIFS due to light fixture relocation - MILLION CONSTRUCTION |  |  | 2009-07-28 | 5030.58
Appl. 16 | 48 | Additional Cost to Furnish and Install handrails and at two Front Entrances - EJ GARRETT WELDING |  |  | 2009-07-28 | 7367.71 | 2009-08-17 | 7367.71
| 49 | Furnish and Install the Additional Signage requested by MVA - SMI SIGN |  |  | 2009-08-07 | 7448.75
Appl 16 | 49A | Furnish and Install the Additional Signage requested by MVA-REVISED - SMI SIGN |  |  | 2009-08-07 | 1874.99 | 2009-08-17 | 1874.99
| 50 | Furnish and Install labor and mateiral to repair walls in Electrical room and laminate 1/4" drywall on plywood in DELPS office SYSTEM "42" |  |  | 2009-08-03 | 1928.83 | 2009-08-10 | 0 |  |  |  | MVA decided not to do
| 51 | Demo and Dispose of Existing Concrete Pad and CMU Wall for Exterior Front Entrance Sign SYSTEM ''42" |  |  | 2009-08-03 | 664.21 | 2009-08-10 | 0 |  |  |  | MVA decided not to do
| 52 | Furnish and Install Door Closures for Three (18) Doors and Provide two additional, as requestedd by MVA - SYSTEM ''42" - BALTIMORE DOOR |  |  | 2009-08-09 | 5627.97
Appl. 16 Allowance 3 | 52A | Furnish and Install Door Closures for Three (3) Doors and Provide two additional, as requestedd by MVA SYSTEM ''42" - BALTIMORE DOOR |  |  | 2009-08-10 | 1440.11 | 2009-08-17 | 1440.11
Appl. 16 | 53 | Remove all Dead Shrubs, Mulch and Seed Areas in Front of Building, as requested by MVA "42"-KELLY TREE & LAWN SERVICE |  |  | 2009-09-22 | 2818.75 | 2009-11-04 | 2818.75
Appl. 16 | 54 | Re-install Section of Wood Fence at Dumpster Area, as requested by MVA "42" LONG FENCE |  |  | 2009-09-22 | 902 | 2009-10-08 | 902
Appl. 16 | 55 | Scrape, Point-up Mortar Joints and Seal Exterior Brick BROWN & SONS |  |  | 2009-10-06 | 3946.25 | 2009-10-08 | 3946.25
Appl. 16 | 56 | Furnish Labor and Material to Install Handrail along the Handicap Ramps DAVE AND PHIL WELDING |  |  | 2009-10-22 | 12126.26 | 2009-11-04 | 14287.94
| 57 | Furnish Labor and Material to wax all new floor areas COMMERCIAL BUILDING MAINTENANCE |  |  | 2009-10-06 | 3946.25
Appl. 16 | 58 | Furnish Labor and Material to Landscape Area in Front of Building KELLY'S TREE AND LANDSCAPING |  |  | 2009-10-28 | 2762.38 | 2009-11-04 | 2762.38
Appl. 16 | 59 | Demo Tile and Install Floor Mat to cover all of Vestibule-1 and Vestibule-2 Entrance MATWORKS |  |  | 2009-10-28 | 1319.18 | 2009-11-04 | 1319.18
Appl. 16 | 60 | Furnish Labor and Material to wax all new floor areas COMMERCIAL BUILDING MAINTENANCE |  |  | 2009-10-22 | 2482.54 | 2009-11-04 | 2482.54

## Million Log In Form
CHANGE ORDER | [5 empty] | PROJECT NAME: | Replace EIFS Building 75 Naval Research Lab Chesapeake Bay , MD |  |  | CONTRAC No.: C10900-S-008
[6 empty] | CLIENT'S NAME AND ADDRESS: | CJW Desbvuild JV LLC 8957 Edmonston Rd - Suite Q Greenbelt, MD 20770 |  |  | PROJECT LOCATION: Naval Research Lab, Chesapeake Bay, MD
Status |  |  | CO # | MCI CO# | DESCRIPTION |  |  | DATE SUBMITTED | AMOUNT OF CHANGE | DATE OF RESPONSE | AMOUNT APPROVED | SCHEDULE IMPACT | No. of Days Requested | No. of Days Approved |  |  | REMARKS
Awaiting Answer | Approved | Rejected | [12 empty] | BILLED | Subcontractor
|  | X |  | 1 | Expansion Joint Protection |  |  | 2014-06-20 | 26976.16 |  |  |  | 4421.6422 |  |  |  |  | 2026-07-28 15:25