## JobStatus
Cost |  | Budget | Completion | Actual | Committed | Forecast | Variance
Category | Description | Cost | % | Cost | Cost | Cost | %
0 | ***CLICK Add-Ins PowerJobCost>Clear Worksheets MENU TO CLEAR DEMO ENTRIES
1 | *** SAMPLE ENTRIES FOR DEMO | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00
11 | Excavation, sitework | 2725.00 | 100.00 | 2300.00 | 2300.00 | 2300.00 | -15.60
12 | Foundations, floor slab | 6725.00 | 100.00 | 7200.00 | 7600.00 | 7600.00 | 13.01
13 | Flatwork, walkways, driveway | 3650.00 | 20.00 | 300.00 | 500.00 | 2500.00 | -31.51
15-PA | Painting | 4200.00 | 10.00 | 310.00 | 310.00 | 3100.00 | -26.19
17 | Finish hardware | 675.00 | 30.00 | 225.00 | 225.00 | 750.00 | 11.11
18-SHOW | Shower and tub, enclosures | 875.00 | 30.00 | 250.00 | 250.00 | 833.33 | -4.76
24-INT | Interior finishes | 5125.00 | 0.00 | 0.00 | 0.00 | 5125.00 | 0.00
28-WI | Wiring | 4500.00 | 20.00 | 0.00 | 700.00 | 3500.00 | -22.22
44 | Final cleanup | 750.00 | 0.00 | 0.00 | 0.00 | 750.00 | 0.00

## InputLog
Input | Cost |  | Budget | Completion | Actual | Committed
Date | Category | Description | Cost | % | Cost | Cost

## QuickHelp
QUICK HELP
How come I do not see the "PowerJobCost" menu inserted among the Excel menu system? | Check the following. 1. Click Tools > Macro > Security. Then click on "Medium" security. 2. Close the PowerJobCost.xls file, then open it again. At startup click on "Enable Macros". Now, you should see the "PowerJobCost" menu inserted among the Excel menu system. >>> For Office 2007-12 In order to see the PowerJobCost menu, click on "Add-Ins" menu of Excel. Then click on "PowerJobCost" to see the menu.
When I open PowerEstimator JobCost Controller, why does a menu called "PowerJobCost" appear in Excel's menu bar? | In order to make our system as easy to use as possible, we added functions to the familiar existing interface, namely the Excel menu bar. The PowerJobCost menu item shall be there *only* when you are using the PowerEstimator JobCost Controller. When you leave, it will disappear.
How do I start a new job? | Click on "Add New Cost Account" from Excel's PowerJobCost menu. Then start entering your PowerJobCost account definitions. Add category (max 8 characters), description (max 50 characters). This will be the account for tracking costs. Note: We provide a sample PowerJobCost file for a typical home construction. If your project is similar, edit this file using "Maintain Cost Account" function. Otherwise, use "Clear Worksheets" to start fresh.
How do I maintain accounts? | Periodically, you should maintain accounts to update expenses, committments, etc. First, place your mouse on the row and select "Maintain Cost Account" from Excel's PowerJobCost menu. Then start entering your PowerJobCost account data. If Budget has changed (perhaps due to change orders), enter change in Budget Cost in the "Change This Period" column. If you have already started a job and expended funds, then also enter "Completion", "Actual Cost" and "Committed Cost".
What is Budget Cost? | Budget Cost is the basis for tracking costs. It usually originates from your estimate. Budget Cost does not change throughout the project unless scope of work changes, e.g. a change order that adds to scope of work.
What is Actual Cost? | Actual Cost is the expended funds for the PowerJobCost item. This figure comes from accounting records.
What is Committed Cost? | Committed Cost is the amount that you are obliged to pay but have not yet paid, e.g. Work done by a subcontractor but not yet invoiced or paid.
What is Completion? | Completion is the percentage of physical completion of the PowerJobCost item at the time of maintaining the PowerJobCost Controller file. For example, if you have 400 Lf of chain link fence to build and you have built 100 Lf in this period, then you enter 25% for completion in this period.
What is Forecast at Completion? | This is the amount that PowerJobCost Controller forecasts to be the total cost to complete the work item 100%. It is derived using your input as well as PowerJobCost Controller's intelligent algorithms.
What is Variance? | Variance is the forecasted difference from budget at job completion. This value can be positive (over budget) or negative (under budget).
How should I save my job setup? | After setting up a PowerJobCost file the first time, save the file under a different name. Use Excel's File > Save As function. From then on, open this saved file for item maintenance.
What is JobStatus worksheet? | PowerEstimator JobCost Controller lists all PowerJobCost entries in the JobStatus worksheet. *Note*: PowerEstimator JobCost Controller maintains this worksheet automatically. Therefore, do not edit or delete rows and columns from this worksheet directly. This may cause errors.
I can't directly add or edit the JobStatus workshet. Why? | Because JobStatus worksheet is protected for edits. Use PowerJobCost menu items to maintain this sheet. If you must unprotect this sheet, use Tools > Protection > Unprotect Sheet function from Excel menu. No password is required. We recommend to keep this sheet protected at all times.
What is InputLog worksheet? | PowerJobCost Controller lists each and every PowerJobCost entry in the InputLog worksheet for audit trail. *Note*: PowerJobCost Controller maintains this worksheet automatically. Therefore, do not edit and modify this worksheet directly.
When should I use Clear Worksheets function from PowerJobCost menu? | When you start a new PowerJobCost file and save it in a different name, you may want to clear the PowerJobCost.xls file worksheets to be ready to start another PowerJobCost project when needed.
After entering I decided not to have the entry as a PowerJobCost item. How can I delete a row from JobStatus worksheet. | Click on the row. Then click on "Delete Row/Cost Account" from PowerJobCost menu. You may not delete a row using Excel's delete function since the worksheet is protected.
How can I get Help? | Click on "Show PowerEstimator JobCost Help" from Excel's PowerJobCost menu.
How do I create PowerJobCost reports? | Select "Create Summary Report" or "Create Detail Report" from the PowerJobCost menu.
Why did the report appear in a different Excel file? | PowerEstimator JobCost Controller creates the reports in a new Excel file so that you can save the report in a different name.
How do I save the PowerJobCost report? | Simply use Excel's Save function.
Can I add rows and edit the PowerJobCost reports? | Yes, you can modify the PowerJobCost reports.
How can I print a PowerJobCost report? | Simply use Excel's Print function.
After the PowerJobCost report is created, how can I go back to PowerJobCost Controller job file? | Click on the minimized PowerJobCost file button from the Taskbar.
How can I learn about program updates? | Visit our website at http://www.powerestimator.com